## Summary
HaqqAI project budget
Funding requested: 50,000,000 naira over 12 months
Category | Amount (₦) | Share of total
Product build out | 20000000 | 40%
Team | 8000000 | 16%
Pilot deployment | 8000000 | 16%
Security, compliance and scale testing | 7000000 | 14%
Infrastructure and operating costs | 5000000 | 10%
Contingency | 2000000 | 4%
Total | 50000000 | 100%
Detail is on the Line Items sheet. Spending by month is on the Monthly Plan sheet.

## Assumptions
Assumptions and notes
Blue cells are inputs and can be changed. Black cells are formulas.
Funding requested (naira) | 50000000
Project length (months) | 12
Notes
1. All amounts are planning estimates in naira.
2. Amounts are treated as including any taxes that apply.
4. The founder's own pay is not paid from this budget.
5. Product build out covers contracted design and development work. The part time engineer and the sales support sit under Team.
6. Recurring costs are spread evenly over their start and end months on the Monthly Plan sheet. One time costs are spread over their stated window.
7. The contingency reserve is shown in the final month. It is spent only if other costs rise.
8. Quantity times unit cost gives each line's total on the Line Items sheet. Change a quantity or unit cost there and every other sheet updates.

## Line Items
Ref | Category | Item | Basis | Qty | Unit | Unit cost (₦) | Total (₦) | Start month | End month
P1 | Product build out | Customer assistant interface | Fixed price project, contracted designer and front end developer. Includes setting the assistant up for the six customer uses and showing the confidence score | 1 | project | 6000000 | 6000000 | 1 | 4
P2 | Product build out | Staff knowledge assistant interface | Fixed price project, built on the same verification engine. Includes the HR, IT, operations, customer service and training uses, and the credit, compliance and regulatory assistants | 1 | project | 5000000 | 5000000 | 3 | 6
P3 | Product build out | Verification trace and audit screens | Screens that show each check and its source page to a reviewer | 1 | project | 2500000 | 2500000 | 5 | 7
P4 | Product build out | Retrieval speed and reliability work | Use stored vectors instead of re-embedding, and make repeat runs give consistent answers | 1 | project | 2000000 | 2000000 | 1 | 3
P5 | Product build out | Filing ingestion and company registry tooling | Lets a new institution's documents be added without engineering help | 1 | project | 2500000 | 2500000 | 2 | 4
P6 | Product build out | UI and UX design, user testing with staff | Design work and two rounds of testing with bank staff | 1 | project | 2000000 | 2000000 | 1 | 3
T1 | Team | Part time software engineer | About 20 hours a week for 10 months. Includes building human escalation and the AML/KYC, risk and fraud assistants in months 9 and 10 | 10 | month | 450000 | 4500000 | 2 | 11
T2 | Team | Sales and partnerships support | Monthly retainer for introductions into banks and fintechs | 9 | month | 300000 | 2700000 | 4 | 12
T3 | Team | Banking compliance advisor | Quarterly retainer | 4 | quarter | 200000 | 800000 | 3 | 12
L1 | Pilot deployment | Integration work for one institution | Connecting to a test environment of the pilot bank's own systems | 1 | project | 4000000 | 4000000 | 6 | 8
L2 | Pilot deployment | Deployment and staff training | Set up at the pilot institution and train its users | 1 | project | 1500000 | 1500000 | 8 | 9
L3 | Pilot deployment | Pilot support and monitoring | Three months of support after go live | 3 | month | 500000 | 1500000 | 9 | 11
L4 | Pilot deployment | Travel and meetings | Visits to the pilot bank and prospective customers in Lagos and Abuja | 1 | lump sum | 1000000 | 1000000 | 4 | 12
S1 | Security, compliance and scale testing | Independent penetration test | External firm, one full test and one retest | 1 | engagement | 2500000 | 2500000 | 7 | 8
S2 | Security, compliance and scale testing | Tenant isolation and load testing | Check that one institution can never see another's data, under load | 1 | project | 1500000 | 1500000 | 6 | 7
S3 | Security, compliance and scale testing | Data protection review and contract templates | Legal review against the Nigeria Data Protection Act, plus a standard data agreement | 1 | engagement | 1800000 | 1800000 | 3 | 5
S4 | Security, compliance and scale testing | Security tooling and audit log storage | Secrets management and separate storage for the audit trail | 1 | setup | 1200000 | 1200000 | 2 | 3
I1 | Infrastructure and operating costs | Cloud hosting | Application, database and vector storage | 12 | month | 200000 | 2400000 | 1 | 12
I2 | Infrastructure and operating costs | Language model usage | Testing, demos and the pilot, billed by the provider | 12 | month | 100000 | 1200000 | 1 | 12
I3 | Infrastructure and operating costs | Software tools and licences | Development, design and project tools | 1 | year | 500000 | 500000 | 1 | 12
I4 | Infrastructure and operating costs | Domain, email, monitoring and backups | Yearly costs | 1 | year | 300000 | 300000 | 1 | 12
I5 | Infrastructure and operating costs | Internet and test devices | Data plan and phones or tablets for testing | 12 | month | 50000 | 600000 | 1 | 12
C1 | Contingency | Contingency reserve | 4% of the total, kept back for cost changes and used only if needed | 1 | reserve | 2000000 | 2000000 | 12 | 12
|  | Total |  |  |  |  | 50000000

## Monthly Plan
Spending by month (₦)
Ref | Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
P1 | Customer assistant interface | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
P2 | Staff knowledge assistant interface | 0 | 0 | 1250000 | 1250000 | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000
P3 | Verification trace and audit screens | 0 | 0 | 0 | 0 | 833333.3333 | 833333.3333 | 833333.3333 | 0 | 0 | 0 | 0 | 0 | 2500000
P4 | Retrieval speed and reliability work | 666666.6667 | 666666.6667 | 666666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
P5 | Filing ingestion and company registry tooling | 0 | 833333.3333 | 833333.3333 | 833333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
P6 | UI and UX design, user testing with staff | 666666.6667 | 666666.6667 | 666666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
T1 | Part time software engineer | 0 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 0 | 4500000
T2 | Sales and partnerships support | 0 | 0 | 0 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 2700000
T3 | Banking compliance advisor | 0 | 0 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 800000
L1 | Integration work for one institution | 0 | 0 | 0 | 0 | 0 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 0 | 0 | 0 | 0 | 4000000
L2 | Deployment and staff training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 1500000
L3 | Pilot support and monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | 1500000
L4 | Travel and meetings | 0 | 0 | 0 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 1000000
S1 | Independent penetration test | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 2500000
S2 | Tenant isolation and load testing | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 1500000
S3 | Data protection review and contract templates | 0 | 0 | 600000 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000
S4 | Security tooling and audit log storage | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
I1 | Cloud hosting | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 2400000
I2 | Language model usage | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
I3 | Software tools and licences | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 500000
I4 | Domain, email, monitoring and backups | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
I5 | Internet and test devices | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
C1 | Contingency reserve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000
| Total for the month | 3250000 | 5133333.3333 | 7063333.3333 | 5541111.1111 | 4041111.1111 | 5524444.4444 | 5524444.4444 | 4691111.1111 | 2607777.7778 | 1857777.7778 | 1857777.7778 | 2907777.7778 | 50000000
| Running total | 3250000 | 8383333.3333 | 15446666.6667 | 20987777.7778 | 25028888.8889 | 30553333.3333 | 36077777.7778 | 40768888.8889 | 43376666.6667 | 45234444.4444 | 47092222.2222 | 50000000